## Roles
CSIS 2430 - 502
Group 2 Project 1: Set Operations
Project Roles
Role | Assigned | Notes
Implementation Lead | Logan Chess
Verification Lead | Julian Cloward
Communications Lead | Alex Branch
Implementation Lead 2 | Justin Omal | Has not made contact with group

## Tasks & Milestones
CSIS 2430 - 502
Group 2 Project 2: Sorting Algorithms
Tasks and Milestones
Deliverable Due Dates (Canvas)
Item | Assigned | Due Date | Status | Status Date | Notes | Evidence Pointer
Weekly Status Report 1 | Individual | 2026-03-08 | Complete | 2026-03-06
Checkpoint | Julian | 2026-03-15 | Complete | 2026-03-15
Weekly Status Report 2 | Individual | 2026-03-15 | Complete | 2026-03-15
Peer Review | Individual | 2026-03-22 | Complete | 2026-03-22
Project Submission | All | 2026-03-22 | Complete | 2026-03-24
Weekly Status Report 3 | Individual | 2026-03-22 | Complete | 2026-03-22
Organizational Tasks & Milestones
Item | Assigned | Due Date | Status | Status Date | Notes | Evidence Pointer
First Project Meet | All | 2026-03-02 | Complete | 2026-03-02
Assign tasks | All | 2026-03-02 | Complete | 2026-03-02
Develop GitHub Repo + Grant accesses | Julian | 2026-03-04 | Complete | 2026-03-02
Create Project Plan | Julian | 2026-03-04 | Complete | 2026-03-04 |  | Commit: 0f2f32f0f8939e76d6c95517528df3be46dfe1ab
Meeting 2 | All | 2026-03-08 | Complete | 2026-03-09 | 7:00pm Weekly
Project Scope | Alex | 2026-03-15 | Complete | 2026-03-09 |  | Commit: abe508908d991dc4e0316e9703f2fd3919fd3001
Meeting 3 | All | 2026-03-15 | Complete | 2026-03-15 | 7:00pm Weekly
Plan screencast logistics | All | 2026-03-15 | Complete | 2026-03-15
Report Outline | Julian | 2026-03-16 | Complete | 2026-03-16 |  | Commit: 97bd8cd7bc7709d04eaba924adf7d7da144f2d46
Contributions Outline | Logan | 2026-03-21 | Complete | 2026-03-21 |  | Commit: 1dfaf00be5cce80b0503e3197fed6785ad72c9cd
Screencast Video | All | 2026-03-21 | Complete
Screencast Project Structure | Julian | 2026-03-21 | Complete | 2026-03-24
Screencast Comparisons | Alex | 2026-03-21 | Complete | 2026-03-21
Screencast Permutation | Alex | 2026-03-21 | Complete | 2026-03-21
Screencast Live run | Logan | 2026-03-21 | Complete | 2026-03-21
Screencast Brief Summary | Logan | 2026-03-21 | Complete | 2026-03-21
Report summary | All | 2026-03-21 | Complete | 2026-03-22
Report Contributions Due | All | 2026-03-21 | Complete | 2026-03-23
Final Report Editing | All | 2026-03-21 | Complete | 2026-03-22
Group meeting 4 | All | 2026-03-21 | Complete | 2026-03-21 | Saturday 7:00pm
Coding Tasks & Milestones
Item | Assigned | Due Date | Status | Status Date | Notes | Evidence Pointer
UML / pseudocode | Logan | 2026-03-08 | Complete | 2026-03-09 |  | Commit: 9e3c761ad1351c342bed733109f54d97e81f00fe
Part 1 Code | Alex | 2026-03-08 | Complete | 2026-03-15
Object class implementations | Alex | 2026-03-08 | Complete | 2026-03-04 |  | Commit: 938aaf9d9abb09484976ad421a0badf3df3cf638
Edge cases / testing | Logan | 2026-03-15 | Complete | 2026-03-15 |  | Commit: 2ab3251fa9b2d9b7ea4fde9390ed53485f65c286
Part 2 Code | Logan & Julian | 2026-03-08 | Complete | 2026-03-15
Merge Sort implementation | Logan | 2026-03-08 | Complete | 2026-03-09 |  | Commit: 6e0303585ead7418220c1b7ede9e210104838d30
Quick Sort implementation | Logan | 2026-03-08 | Complete | 2026-03-09 |  | Commit: 7392e70057701b17c21dfc0b4a10bcb2a66f8195
Shaker Sort implementation | Julian | 2026-03-08 | Complete | 2026-03-09 |  | Commit: 20451d3bd044280e478a959ef5ce325c571250be
Heap Sort implementation | Julian | 2026-03-08 | Complete | 2026-03-09 |  | Commit: 20451d3bd044280e478a959ef5ce325c571250be
Edge cases / testing | Logan | 2026-03-15 | Complete | 2026-03-15 |  | Commit: 2ab3251fa9b2d9b7ea4fde9390ed53485f65c286
Part 3 Code | Alex | 2026-03-15 | Complete | 2026-03-11 |  | Commit: 88c71e776d8195de46ff34ecdc2bdb1d25930e2d
Part 4 Code | Logan | 2026-03-15 | Complete | 2026-03-15 |  | Commit: 20c2f439db54f202c5fe416ec6a81eb660482410
Final code merged on main branch | All | 2026-03-15 | Complete | 2026-03-15
README documentation | Julian | 2026-03-22 | Complete | 2026-03-22 |  | Commit: 2b8e3ceeb14ab68acd05f1a2cc19283b36dec617
Report Writing Assignments
Item | Assigned | Due Date | Status | Status Date | Notes | Evidence Pointer
Introduction | Alex | 2026-03-21 | Complete | 2026-03-21 |  | Commit: 8dfb9ab2dbd0b928564f1b64efb2b5b00f3a7826
Algorithm Summaries | Alex | 2026-03-21 | Complete | 2026-03-21 |  | Commit: 8dfb9ab2dbd0b928564f1b64efb2b5b00f3a7826
Methods | Alex | 2026-03-21 | Complete | 2026-03-21 |  | Commit: 8dfb9ab2dbd0b928564f1b64efb2b5b00f3a7826
Results | Logan | 2026-03-21 | Complete | 2026-03-21 |  | Commit: e498ba675921640d726b4f4e3584dc916b78c91a
Discussion-1 | Julian | 2026-03-21 | Complete | 2026-03-21 |  | Commit: db9f858b65b4748264e9546aa6c7957f68476f15
Discussion-2 | Julian | 2026-03-21 | Complete | 2026-03-22 |  | Commit: 3b5082e94c2c45e38a81edcc30bd1599c97cef68
Discussion-3 | Logan | 2026-03-21 | Complete | 2026-03-21 |  | Commit: e498ba675921640d726b4f4e3584dc916b78c91a
Discussion-4 | Logan | 2026-03-21 | Complete | 2026-03-21 |  | Commit: e498ba675921640d726b4f4e3584dc916b78c91a
Discussion-5 | Julian | 2026-03-21 | Complete | 2026-03-22 |  | Commit: 3b5082e94c2c45e38a81edcc30bd1599c97cef68
Conclusion | Alex | 2026-03-21 | Complete | 2026-03-22 |  | Commit: cbee49782bce74e1aac0a84f2978de9e92ff2943
Lessons Learnd | Alex | 2026-03-21 | Complete | 2026-03-22 |  | Commit: cbee49782bce74e1aac0a84f2978de9e92ff2943